## Master To-Do
Sentinel / CRR Use Case — Master To-Do List (seed)
Seeded 8/20/2026 from artifact inventory + OCTO items. Paste rows into your template as needed.
Stream | Task | Notes | Status | Priority | Due | Owner
Admin
Admin | Stand up artifact inventory tracker | Delivered 8/20; keep current as items progress. | Done
Admin | Set up master to-do list with streams | This list. | In progress | High
Admin | Establish project status update cadence | Recurring status notes to your management / project sponsor. | Not started | Medium
Governance & Risk
Governance & Risk | Register parallel OCTO case | AI use case registration in OCTO. | Done
Governance & Risk | Finish governance process in OCTO | Complete remaining OCTO workflow steps for the CRR use case. | In progress | High
Governance & Risk | Draft AI/model risk use-case documentation | Risk assessment, human-in-the-loop controls, reviewer attestation requirements. | Not started | High
Governance & Risk | Define records retention & audit trail requirements | How platform-produced workpapers are retained; required audit trail. | Not started | Medium
Governance & Risk | Map to Interagency Guidance on Credit Risk Review Systems | Show independence and coverage are preserved. | Not started | Medium
Content Assembly
Content Assembly | Build workpaper type inventory & content ownership matrix | Every workpaper type, by section, with owning team/role per content area. | Not started | High
Content Assembly | Draft house style writing guide | Voice, tone, terminology, formatting conventions. | Not started | High
Content Assembly | Compile policy reference corpus & policy-to-workpaper mapping | Minimum: listing of which policies apply to which workpaper types. | Not started | High
Content Assembly | Define policy corpus operating model | Owner, refresh cadence, versioning, effective dates. | Not started | Medium
Content Assembly | Assemble gold-standard exemplar workpapers | Sanitized 'what great looks like' examples per type; doubles as QA benchmark. | Not started | High
Content Assembly | Create canonical annotated templates | Per section: system-drafted vs. analyst judgment vs. data-fed. | Not started | Medium
Content Assembly | Build source data inventory | Systems/documents feeding each workpaper section and how accessed. | Not started | Medium
Content Assembly | Compile glossary & definitions | Risk ratings, regulatory classifications, house acronyms. | Not started | Low
Quality & Testing
Quality & Testing | Document workpaper review standards | Standards completed workpapers are reviewed against. | Not started | High
Quality & Testing | Define definition of done / acceptance criteria | Per workpaper type: what a platform draft must meet before an analyst works from it. | Not started | Medium
Quality & Testing | Build evaluation rubric & error severity taxonomy | Scoring framework; error classes ranked by severity. | Not started | Medium
Quality & Testing | Assemble golden test set | Sanitized real cases with known-correct outcomes for UAT/regression. | Not started | Medium
Quality & Testing | Develop UAT plan & test scripts | Derived from the end-user process walkthrough. | Not started | Medium
Training & Enablement
Training & Enablement | Draft full CRR end-user process walkthrough | The detailed analyst-facing guide; the short-form journey doc is its seed. | Not started | High
Training & Enablement | Create quick reference guides / FAQ | One-page job aids distilled from the walkthrough. | Not started | Low
Training & Enablement | Plan & deliver analyst training | Sessions ahead of pilot/go-live. | Not started | Low
Coordination
Coordination | Send short-form CRR analyst user journey to IT | 'What does a CRR analyst even do' — basis for IT planning. Draft in hand; tailor and send. | In progress | High | 8/20/2026
Coordination | Review BRD for CRR gaps; feed back to IT | Confirm the BRD covers CRR needs; log gaps. | Not started | High
Coordination | Build BRD requirements traceability matrix | CRR requirements mapped to BRD coverage so gaps surface before UAT. | Not started | Medium
Coordination | Start shared-vs-tenant asset decision log | Which assets are platform-wide vs. CRR-owned; coordinate with other two tenants. | Not started | Medium
Rollout & Adoption
Rollout & Adoption | Capture baseline metrics | Time-per-workpaper, rework/re-review rates — must happen pre-launch. | Not started | High
Rollout & Adoption | Select pilot group | Named pilot users. | Not started | Medium
Rollout & Adoption | Stand up feedback/triage loop | Route bad outputs to fixes. | Not started | Medium
Rollout & Adoption | Assign owner & refresh cadence per artifact | So the style guide, corpus, matrices don't go stale. | Not started | Low
Streams: file each task by what it unblocks, not what it touches. Shaded rows are stream headers. Status/Priority have dropdowns.