## Artifact Inventory
CRR Use Case — Artifact Inventory & Tracker
Sentinel shared capability platform · Credit Risk Review tenant
Category | Item | Description | Status | Owner | Priority | Target Date | Notes
Process & Training
Process & Training | CRR end-user process walkthrough | Step-by-step guide showing how a CRR analyst uses the platform end-to-end: initiating a workpaper, reviewing and editing drafts, finalizing and routing for review. | Not started |  |  |  | On Steve's initial list
Process & Training | Quick reference guides / FAQ | One-page job aids and FAQs distilled from the walkthrough for day-to-day use after initial training. | Not started
Content & Grounding
Content & Grounding | Workpaper type inventory & content ownership matrix | Catalog of every CRR workpaper type, broken down by section, with the owning team/role for each content area. | Not started |  |  |  | On Steve's initial list
Content & Grounding | House style writing guide | Voice, tone, terminology, and formatting conventions that all written work product (and platform drafts) must follow. | Not started |  |  |  | On Steve's initial list
Content & Grounding | Policy reference corpus & mapping | At minimum, a listing of which policies apply to which workpaper types; ideally the full corpus itself, versioned. | Not started |  |  |  | On Steve's initial list
Content & Grounding | Policy corpus operating model | Who refreshes the policy corpus, on what cadence, with version control and effective-date tracking. | Not started
Content & Grounding | Gold-standard exemplar workpapers | Sanitized examples of excellent completed workpapers per type; serves as grounding material and as the QA benchmark. | Not started
Content & Grounding | Canonical annotated templates | Official template per workpaper type, annotated by section: system-drafted vs. analyst judgment vs. data-fed. | Not started
Content & Grounding | Source data inventory | The systems and documents that feed each workpaper section (loan system, spreads, appraisals, credit agreements) and how each is accessed. | Not started
Content & Grounding | Glossary & definitions | Risk rating definitions, regulatory classification definitions (pass, special mention, substandard), and house acronyms. | Not started
Quality & Acceptance
Quality & Acceptance | Workpaper review standards | The standards completed workpapers are reviewed against; defines what acceptable finished work looks like. | Not started |  |  |  | On Steve's initial list
Quality & Acceptance | Definition of done / acceptance criteria | Per workpaper type, the criteria a platform draft must meet before an analyst can work from it. | Not started
Quality & Acceptance | Evaluation rubric & error severity taxonomy | Scoring framework for platform output quality, with error classes ranked by severity (factual misstatement vs. style deviation). | Not started
Quality & Acceptance | Golden test set | Sanitized real cases with known-correct outcomes, used for UAT and ongoing regression checking. | Not started
Quality & Acceptance | UAT plan & test scripts | Test scenarios for the CRR use case, derived from the end-user process walkthrough. | Not started
Governance & Compliance
Governance & Compliance | AI / model risk use-case documentation | Use-case risk assessment, human-in-the-loop control description, and reviewer attestation requirements. | Not started
Governance & Compliance | Records retention & audit trail requirements | How platform-produced workpapers are retained and what audit trail must exist for them. | Not started
Governance & Compliance | Regulatory guidance mapping | Mapping to the Interagency Guidance on Credit Risk Review Systems showing independence and coverage are preserved. | Not started
Adoption & Operating Model
Adoption & Operating Model | Baseline metrics capture | Pre-launch measurement of time-per-workpaper and rework/re-review rates, so the platform's impact can be demonstrated later. | Not started
Adoption & Operating Model | Pilot group & feedback loop | Named pilot users plus a triage process so bad outputs route to fixes instead of hallway complaints. | Not started
Adoption & Operating Model | Shared-vs-tenant asset decision log | Record of which assets are platform-wide vs. CRR-owned, coordinated with the other two tenants. | Not started
Adoption & Operating Model | BRD requirements traceability matrix | Mapping of CRR requirements to what the BRD actually covers, so gaps surface before UAT. | Not started
Adoption & Operating Model | Artifact ownership & refresh cadence | Named owner and update cycle for every artifact in this inventory, so none of it goes stale. | Not started
How to use: fill in Status (dropdown), Owner, Priority (dropdown), and Target Date for each item. Shaded rows are category headers — no tracking needed.